## Sheet1
Date	WORK	BREAKTHROUGH
April 3rd 2017	IOT plan to work on connection oriented data write and read	ctl+enter for newline
	Removed BOOST error or Whenever removed “Out” folder by manually	“scons -c”
	created script file to scons and run ./m.bat and ./r.bat
	“extern” keyword is used to link any variable throught the scope of the application
	XPLANNER LOGINhttp://192.168.4.7:8899/xplanner-plus/do/login	user_name: pujalashPassword: ashok

APRIL 4th 2017	ADDED filter functions to Detect duplicate address and avoid them...,	done

April 5th 2017	Made IOT application to detect BLE devices only by modifying “setdiscoveryfilter” by Modifying the transport type in the parameters it is using...	done

April 6th 2017	Worked on Non-IOTivity ble characteristic table forming and optimising the performance	done

April 7th 2017	Working on demo illustration setup to present...
	Got comment from the manager, about maintaining coding standards as i am not / Maintaining those standards...	Postponed

April 10th 2017	Working on maintainig coding standards from the book mailed by manager	done
	working on Sensor Tag Detection in the raspberry	Need Cold restart for raspberry for detection of every devices

April 24th 2017	Push working code of DM into GIT repository with standard coding of DM excluding / Non-iotivity.c file with Get, Put Working( Bug fixed code )	Done
	Implementing TERMINATE Feature

April 26th 2017	Sync among GET, PUT, OBSERVE
	Bus error

April 26th 2017	STILL Bus Error

May 1st 2017	Session on QMS	done
	Assigned task of DM API clean up at evening

May 2nd 2017	DM API clean up	done

May 3rd 2017	DM API layer clean up	still pending

May 4th 2017	DM API layer clean up(still pending)	done

May 5th 2017	DM API Delete (New feature integration)	Done

May 8th 2017	Getting Involved in IOTivity	Done
	Documentation on it	Done

May 9th 2017	No work
	Learning new concepts (how linux works)

may 10th 2017	LEAVE

May 11th 2017	Observe task assigned and unassigned
	Working on Bus ERROR

May 12th 2017	Working on tasks(Investigation on BUS ERROR) assigned by Mohan	comment from Project Lead: 1) Me Lacks Innovation
Friday	Task1 : DM with IP(No BLE)	2) Not working towards the way youre supposed to.
	Task2 : DM with BLE(No NON-IOTivity BLE)	3) No proper guidance on your own
	Task3 : Combination of above two tasks
	Task4 : DM with NON-IOTivity only (if error persists, then TASK 5)
	Task5 : Consider the IOT BLE packet from working IOTivity, Then use this / Dummy packet as up packete for each Non-Iotivity

may 15th 2017 – / May 19th 2017	TASK: Sync among Get, Put, Observe from non-iotivity side....,	complete: May 19th 2017 with no issues

May 22th – 25th 2017	TASK: IOTIVITY BLE Observe implementation.	done for ALONE IOTIVITY(Need to test Integrity)
	Shell Script to enable automatic mail when an event occurs....

May 26th 2017	Leave

May 29th 2017	working on Implementing Terminate Feature	Some observations done

May 30th 2017	Working on segmentation on discovery for second time
to
June 2nd 2017		completed on today with testing

June 5th 2017 to	working on Terminate Feature
June 7th 2017		completed on today with push to git

June 8th 2017	Checking on flaws
June 9th 2017	Checking on flaws